## ProjectSchedule
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Obtayn
Enter Company Name in cell B2. | Akhil Suresh
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. | Divya Kulkarni | Project Start: |  | 2021-03-31
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-03-29 to 2021-05-23
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-03-29 to 2021-05-23
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Setup + Learning | Akhil, Divya
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Get familiar with Firebase & write POCs |  | 100% | 2021-03-31 | 2021-04-02 | 3
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Get familiar with Firestore & write POCs |  | 100% | 2021-03-31 | 2021-04-02 | 3
| Get familiar with Redux |  | 100% | 2021-03-31 | 2021-04-02 | 3
| React external libraries |  | 100% | 2021-03-31 | 2021-04-02 | 3
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Sign Up form | Akhil
| Create Sign Up component |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Create Sign Up form with fields |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Create "Continue with Google" |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Validate user inputs , show error if invalid inputs. |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Write a function to add user and validate email |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Write a a function to redirect to Login if Sign Up is successful |  | 100% | 2021-04-06 | 2021-04-06
Sample phase title block | Login Page | Akhil
| Create a Login Component |  | 100% | 2021-04-06 | 2021-04-06 | 1
| Create a Login form with fields |  | 100% | 2021-04-06 | 2021-04-06 | 1
| Create a "Continue with Google" button |  | 100% | 2021-04-06 | 2021-04-06 | 1
| Validate user inputs |  | 100% | 2021-04-06 | 2021-04-06 | 1
| Write a function to authenticate User |  | 100% | 2021-04-06 | 2021-04-06
| Write a function to authenticate Google user |  | 100% | 2021-04-06 | 2021-04-06
| Write a function to create Protected Route |  | 100% | 2021-04-07 | 2021-04-07
| Write a a function to redirect to Homepage if Login is successful |  | 100% | 2021-04-07 | 2021-04-07
Sample phase title block | Homepage | Divya
| Create a Header component |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Create "Create a Post" component |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Create a Feed component |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Create a Recent Activity component |  | 100% | 2021-04-05 | 2021-04-05 | 1
| Write a a function to fetch all the required data |  | 100% | 2021-04-12 | 2021-04-12
| Write a function to redirect to Request from Header |  | 100% | 2021-04-05 | 2021-04-05
| Write a function to redirect to Homepage |  | 100% | 2021-04-05 | 2021-04-05 | 1
This is an empty row | Search | Divya
| Create a search component (drop down list of categories, textbox for keyword, location picker) |  | 100% | 2021-04-06 | 2021-04-06
| Load all the categories to show in drop down. |  | 100% | 2021-04-06 | 2021-04-06
| Write a function to show relevant requests as search results. |  | 100% | 2021-04-22 | 2021-04-22
| Write a function to handle “Network Error” exception. |  |  | 2021-04-23 | 2021-04-23
| Write a function to handle “No match found” exception. |  | 100% | 2021-04-22 | 2021-04-22
| Profile | Divya
| Create a Profile component |  | 100% | 2021-04-07 | 2021-04-07
| Write a function to display the Profile Details. |  | 100% | 2021-04-08 | 2021-04-08
| Write a function to load Profile details into the pop-up window. |  | 100% | 2021-04-08 | 2021-04-08
| Write a function to verify new profile image (extension, size). |  | 100% | 2021-04-08 | 2021-04-08
| Write a function to update profile picture |  | 100% | 2021-04-07 | 2021-04-07
| Logout | Divya
| Write a function to logout User |  | 100% | 2021-04-08 | 2021-04-08
| Feed | Divya
| Create Post component |  | 100% | 2021-04-09 | 2021-04-09
| Create Request component |  | 100% | 2021-04-09 | 2021-04-09
| Create a Filter component (Requests and appreciation posts) |  | 100% | 2021-04-12 | 2021-04-12
| Create a Feed component (Filter, multiple Post and Request components) |  | 100% | 2021-04-09 | 2021-04-09
| Create a “Back to Top” button. |  | 100% | 2021-04-12 | 2021-04-12
| Write a function to make the “Back to Top” button. |  | 100% | 2021-04-12 | 2021-04-12
| Write a function to go back to top of the page when “Back to Top” button is clicked |  | 100% | 2021-04-12 | 2021-04-12
| Write a function to fetch all Posts and use the data for the Post component. |  | 100% | 2021-04-12 | 2021-04-12
| Write a function to fetch all pending requests and use it for Request component |  | 100% | 2021-04-12 | 2021-04-12
| Write a function to store all posts and requests in array of objects, sorted by timestamp |  | 100% | 2021-04-12 | 2021-04-12
| Write a function to load all the Feed components. |  | 80% | 2021-04-12 | 2021-04-12
| Create Request | Akhil
| Make a component for request form |  | 100% | 2021-04-07 | 2021-04-07
| Write a function to trigger the modal on click for Create Post component. |  | 100% | 2021-04-07 | 2021-04-07
| Write a function to validate whether form fields are filled. |  | 100% | 2021-04-08 | 2021-04-08
| Write a function to show request form or appreciation form depending on Tag |  | 100% | 2021-04-07 | 2021-04-07
| Write a function to validate image constraints. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to add the new Request when the Post button is clicked. |  | 100% | 2021-04-07 | 2021-04-07
| Write a function to show the new Request on top of the Feed. |  | 100% | 2021-04-08 | 2021-04-08
| Write a function to handle “Network Error” exception. |  |  | 2021-04-23 | 2021-04-23
| Write a function to close the Create Post modal when the “Add Request” button is clicked. |  | 100% | 2021-04-07 | 2021-04-07
| Accept Request | Akhil
| Make a function to change the status of the Request on click of accept button. |  | 100% | 2021-04-12 | 2021-04-12
| Make a function to handle cases of already accepted requests. |  | 100% | 2021-04-12 | 2021-04-12
| Make a function which adds a notification. |  | 100% | 2021-04-12 | 2021-04-12
| Make a function to add Users to the Chat list. |  | 100% | 2021-04-15 | 2021-04-15
| Make a function to redirect to the Requests page. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to highlight current Request. |  | 100% | 2021-04-21 | 2021-04-21
| Delete Request | Akhil
| Write a function to show a confirm box when the delete icon is pressed. |  | 100% | 2021-04-15 | 2021-04-15
| Write a function to delete the request from the database. |  | 100% | 2021-04-15 | 2021-04-15
| Write a function to add a “Request Deleted” notification. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to refresh the Feed page. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to redirect User to the Request page |  |  | 2021-04-21 | 2021-04-21
| Write a function to show a confirm box when the “Cancel” button is pressed. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to remove the request from the Requestor’s “Outgoing” and travellers “Incoming” request. |  | 100% | 2021-04-21 | 2021-04-21
| Recent Activity | Divya
| Use Recent Activity component |  | 100% | 2021-04-13 | 2021-04-13
| Write a function to fetch notifications for current User. |  | 100% | 2021-04-13 | 2021-04-13
| Write a function to display fetched Activity objects in “Recent Activity” sorted by timestamp. |  | 100% | 2021-04-13 | 2021-04-13
| Create chat notification component (clickable) |  | 100% | 2021-04-14 | 2021-04-14
| Create a request update notification component (clickable) |  | 100% | 2021-04-14 | 2021-04-14
| Write new Post | Divya
| Write a function to trigger “Create Post” modal on click. |  | 100% | 2021-04-14 | 2021-04-14
| Create Tag component (request post or appreciation post) |  | 100% | 2021-04-14 | 2021-04-14
| Make a component for appreciation post form |  | 100% | 2021-04-14 | 2021-04-14
| Make a function to validate image size and extension |  |  | 2021-04-22 | 2021-04-22
| Write a function to show request form or appreciation form depending on Tag |  | 100% | 2021-04-14 | 2021-04-14
| Write a function to add the new appreciation post on click of Post button |  | 100% | 2021-04-15 | 2021-04-15
| Write a function to close the Create Post modal when the “Add Post” button is clicked. |  | 100% | 2021-04-15 | 2021-04-15
| Write a function to show the new Post on top of the Feed. |  | 100% | 2021-04-15 | 2021-04-15
| Write a function to handle “Network Error” exception. |  |  | 2021-04-23 | 2021-04-23
| Delete Post | Divya
| Write a function to show a confirm box when the delete icon is pressed. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to delete the post from the database. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to refresh the Feed page. |  | 100% | 2021-04-21 | 2021-04-21
| Write a function to show a confirm box when the “Cancel” button is pressed. |  | 100% | 2021-04-21 | 2021-04-21
| Filter | Akhil
| Create filter options - #request & #appreciation. |  | 100% | 2021-04-16 | 2021-04-16
| Write a function to fetch the selected option. |  | 100% | 2021-04-16 | 2021-04-16
| Write a function to filter the feed by only showing selected option |  | 100% | 2021-04-16 | 2021-04-16
| Write a function to handle user location |  |  | 2021-04-24 | 2021-04-24
| Write a function that takes requests location and user location and sorts the array by nearest to farthest |  |  | 2021-04-24 | 2021-04-24
| View All Requests | Divya
| Create Requests container (Incoming & Outgoing) |  | 100% | 2021-04-16 | 2021-04-16
| Create Incoming requests component with details - requestor, title, location, message, images(if any). |  | 100% | 2021-04-16 | 2021-04-16
| Create Outgoing requests component with details - acceptor, title, location, message, images(if any), Fulfilled button(only for accepted requests),cancel button |  | 100% | 2021-04-16 | 2021-04-16
| Write a function to fetch all the Requests related to the user. |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to display all the fetched Requests. |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to differentiate Outgoing requests depending upon status(accepted/pending). |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to refresh status of Outgoing requests (from pending to accepted). |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to handle Fulfilled button click - show prompt to confirm whether User wants to continue, delete Request if yes. |  | 100% | 2021-04-20 | 2021-04-20
| View Chat List | Akhil
| Create a Chats component to the right of Requests. |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to redirect to the Requests page when the User clicks on the Chats button (available on the header) |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to fetch all User Chats. |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to group messages by different users |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to fetch user profiles and names. |  | 100% | 2021-04-19 | 2021-04-19
| Write a function to make Chat component |  | 100% | 2021-04-20 | 2021-04-20
| Write a function to highlight unread chat in bold. |  | 100% | 2021-04-21 | 2021-04-21
| View Chat Thread | Akhil
| Write a function to switch from the Chat List to Personal Chat. |  | 100% | 2021-04-20 | 2021-04-20
| Write a function which uses data fetched in Story #13, and display the corresponding message thread. |  | 100% | 2021-04-20 | 2021-04-20
| Make a function to display the message thread, such that one can differentiate sender’s and receiver’s messages, with timestamps. |  | 100% | 2021-04-20 | 2021-04-20
| Write a function to scroll down on a new message. |  | 100% | 2021-04-21 | 2021-04-21
| Create a component which contains a text field for text message, file selector for attaching images and a button to send the message. |  | 100% | 2021-04-21 | 2021-04-21
| Create a back button which redirects Users to a list of chats. |  | 100% | 2021-04-21 | 2021-04-21
| Write function to handle “Network Error” exception. |  |  | 2021-04-23 | 2021-04-23
| Write function to check whether selected image fits within constraints (size, file type, number of images selected) |  |  | 2021-04-23 | 2021-04-23
Insert new rows ABOVE this one
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. TimeSheet About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.